## Project Plan
Project Title | Shiv Sena Website Revamp | Company Name | Shiv Sena
Date | 11th May 2026
Step | Task | Start Date | End Date | Status
1.1 | Requirement Gathering & Planning | 4th May | 5th May | In Progress
1.2 | Sitemap Finalization | 5th May | 7th may | Completed
1.3 | Wireframe Creation | 7th May | 8th May | Completed
1.4 | Content Gathering | 11th May | 15th May | In Progress
1.5 | Homepage UI Design | 15th May | 21st May | In Progress
1.6 | Video Banner UI Integration | 20th May | 21st May | In Progress
1.7 | Entry Animation Experience Design | 21st May | 25th May | In Progress
1.8 | Leadership Section UI | 25th May | 27th May | Pending
1.9 | News & Media UI | 27th May | 28th May | Pending
1.10 | Social Feed Integration UI | 29th May | 1st June | Pending
1.11 | Office Locator UI | 2nd June | 4th June | Pending
1.12 | Membership & Join Form UI | 5th June | 8th June | Pending
1.13 | Declaration Form UI | 9th June | 10th June | Pending
1.14 | Accessibility Features Planning | 11th June | 12th June | In Progress
1.15 | Mobile Responsive UI | 15th June | 19th June | Pending
1.16 | Frontend Development | 15th May | 19th June | In Progress
1.17 | CMS & Backend Development | 20th June | 3rd July | Pending
1.18 | Testing & QA | 6th July | 9th July | Pending
1.19 | Accessibility Testing | 11th July | 12th July | Pending
1.20 | Client Review & Final Approval | 13th July | 15th July | Pending
1.21 | Website Deployment | 16th July | 16th July | Pending